## Product Roadmap 2015
2016
TUM IDP Roadmap | Phase 1 |  | Phase 2 |  | Phase 3
| April 1-15 | April 16-30 | May 1 -15 | May 16-31 | June 1-15 | June 16-30
ANALYSIS AND REQUIREMENTS
Akash Manjunath | Create Overall Design Structure
Create Balsamiq Mockups
DESIGN
ER-Model - Prateek Bagrecha | Create comparison between Mongo DB and MySQL | Create basic database based on initial analysis and export for common use
Web-App Architecture - Akash Manjunath |  | Create basic project structure, create github repo, create heroku account and host for common use
IMPLEMENTATION
Backend MVC + Database - Prateek Bagrecha |  |  | Create services using spring
Frontend - Akash Manjunath |  |  | Create webapplication using angularjs or any other appropriate frameworrk
INTEGRATION / TESTING
Integration - Akash Manjunath |  |  |  |  | Integrate Web Application with services and host
Testing - Prateek Bagrecha |  |  |  |  | Perform end to end testing of the system
Final Testing and Sign off
Christian Ruf |  |  |  | Code inspection and feedback | Final Inspection and Sign off
LEGEND:
TASKS COMPLETED
TASKS IN PROGRESS
TASKS YET TO BE STARTED

## Roadmap 2014
| 2014 | [11 empty] | 2015 | [11 empty] | 2016
[Company] - [Team] Roadmap | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Product Track | Project |  |  |  | Project
This is a description of a specific Product Track, which could be your "Site Redesign" projects or something more specific like "User Onboarding and Registration". | Project |  |  |  |  | Project
|  | Project | Project | Project |  | Project | Project
Theme |  | Project |  | Project | Project
You could also use themes and break the roadmap by "Monetization", "Growth" or "Infrastructure Projects" | Bigger Project |  |  |  |  | Project
|  |  |  | Project | [15 empty] | We are too far out to have this be smaller projects (see comment).
Specific Product | Project |  | Project | Another bulky project | [21 empty] | Yes, you should still be trying to plan for all the way out here.
These projects just focus on specific product or feature. | Project
Various Initiatives | Project |  | Project |  | Project | [24 empty] | Nothing wrong with trying to imagine what it will be like a few years from now.
It could be that you still want to capture smaller projects in somewhat of a "miscelaneous" section, but consider how do they fit in the above tracks. If they don't - do you really need to build them? | Project |  |  |  |  | Project
| Project |  |  |  |  | Project
| 2014 Q1 Outcomes |  |  | 2014 Q2 Outcomes |  |  | 2014 Q3 Outcomes |  |  | 2014 Q4 Outcomes |  |  | 2015 Q1-Q2 Outcomes | [5 empty] | 2015 Q3-Q4 Outcomes | [5 empty] | 2016 Q1-Q2 Outcomes | [5 empty] | 2016 Q3-Q4 Outcomes
Exmaple: Complete all new landing pages for paid acquisition
Example: Create a growth channel by rolling out Product X
[11 empty] | 2014 Goals | [11 empty] | 2015 Goals | [11 empty] | 2016 Goals
[11 empty] | Customers | ######## | [10 empty] | Customers | ######## | [10 empty] | Customers | ########
[11 empty] | Revenue | $####### | [10 empty] | Revenue | $####### | [10 empty] | Revenue | $#######

## Projects (hidden)
Project | Description | Timeline
Project 1 | Project 1 description | Q1 2014
Project 2 | Project 2 description | Q2 2014
Project 3 | Project 3 description | Q3 2014
Project 4 | Project 4 description | Q4 2014
Project 5 | Project 3 description | Q1 2015
Note
It's nice to take the time and actually put some meat on the projects with descriptions. You could then use these descriptions to creat the comments for the "hover explantions" on main sheet.